Week 1 Task

# Strategic Agribusiness Data Analysis & Forecasting Plan

A Structured Plan for Collecting and Analysing Public Agribusiness Data to Forecast Agricultural Market Trends

| Detail | Information |
| --- | --- |
| Submitted by | Palarapu Harshavardhan Reddy |
| Role | Intern |
| Task | Week 1 – Agribusiness Data Analysis Planning |
| Deliverable | Comprehensive plan: research rationale, data sources, metrics, process and timeline |

# 1. Objective

The aim of this task is to develop a structured plan for collecting and analysing publicly available agribusiness data. The plan outlines the key indicators, reliable data sources and suitable analysis methods needed to forecast market trends in agriculture, and sets out a realistic timeline with milestones for completing each stage of the work.

## 1.1 Goals of the Plan

- Identify trustworthy public data sources on agriculture production, prices and resource use.

- Define the key metrics (crop yields, pricing dynamics and resource utilization) to be analysed.

- Describe a step-by-step process for data collection, cleaning and interpretation.

- Select forecasting methods suited to agricultural time-series data.

- Provide a timeline with clear milestones and deliverables.

# 2. Research Rationale

Agribusiness covers the whole value chain: inputs such as seed, fertiliser and water, farming, processing, storage, trading and retail. It is highly sensitive to weather, input costs, government policy and global demand. Better forecasting of yields and prices directly helps farmers decide what to plant, helps traders and processors plan procurement, and helps policymakers manage food security and stock levels.

Large volumes of agricultural data are published free by international organisations and national governments. However, this data is scattered across portals, uses different formats and units, and often has gaps. A planned, documented approach is therefore essential to turn raw public data into reliable, decision-ready insight.

## 2.1 Key Research Questions

- How have crop yields and production changed over the last 10 to 20 years, and what drives these changes?

- How do market prices move seasonally, and how do they respond to weather, supply and input costs?

- How efficiently are land, water and fertiliser being used for each crop?

- Which forecasting methods give the most accurate short- and medium-term predictions of prices and yields?

## 2.2 Scope

In scope: publicly available data on major crops (for example rice, wheat, maize, pulses, oilseeds and cotton), at national and state or regional level, covering roughly the last 10 to 20 years.

Out of scope: private or paid datasets, farm-level proprietary records and real-time trading systems.

# 3. Public Data Sources

The sources below are free, official and regularly updated. Each is matched to the kind of information it provides.

| Source | Data Available | Use in This Project |
| --- | --- | --- |
| FAOSTAT (FAO, UN) | Global crop production, area harvested, yield, trade, producer prices, fertiliser and land use | Long-term yield and production trends; international comparison |
| USDA (NASS, ERS, FAS/PSD) | Crop production, supply and demand estimates, prices received, trade statistics | Benchmark data and global market outlook |
| World Bank Open Data / Commodity Markets (Pink Sheet) | Agricultural indicators, monthly commodity price series | Global price benchmarks and macro context |
| Ministry of Agriculture & Farmers Welfare, India (DA&FW, Agricultural Statistics at a Glance) | Area, production and yield by state and crop; minimum support prices | State-level production and policy analysis |
| Agmarknet / e-NAM | Daily mandi arrivals and modal, minimum and maximum prices | Pricing dynamics and seasonality |
| data.gov.in (Open Government Data) | Datasets on crops, rainfall, soil health, irrigation and fertiliser use | Resource utilization and regional comparison |
| India Meteorological Department (IMD), NASA POWER, Open-Meteo | Rainfall, temperature, humidity and solar radiation | Weather features that influence yield and price |
| IMF Primary Commodity Prices; FAO Food Price Index | Monthly global food and commodity price indices | Long-term price trends and volatility |
| APEDA and other trade portals | Agricultural export and import volumes and values | Demand-side and trade influences |
| Kaggle / UCI repositories | Cleaned agriculture datasets for practice | Prototyping and testing models |

## 3.1 Source Evaluation Criteria

- Credibility: official or internationally recognised publisher.

- Coverage: enough years, crops and regions for trend analysis.

- Frequency: daily, monthly or annual data matching the forecast horizon.

- Accessibility: downloadable as CSV, Excel or via an API, with licence terms that allow use.

- Quality: clear definitions, units and documentation, with limited missing values.

# 4. Key Metrics and Indicators

The analysis will focus on three groups of indicators, supported by external factors that help explain and predict changes.

## 4.1 Crop Yields and Production

- Yield per hectare (tonnes/ha) by crop, year and region.

- Total production (tonnes) and area under cultivation (hectares).

- Year-on-year growth rate and variability (standard deviation or coefficient of variation) of yield.

- Cropping intensity and share of irrigated area.

## 4.2 Pricing Dynamics

- Farm-gate, wholesale (mandi) and retail prices per quintal or tonne.

- Monthly and seasonal price index, and price spread between markets.

- Price volatility (rolling standard deviation) and trend direction.

- Minimum support price versus market price, and import/export parity prices.

## 4.3 Resource Utilization

- Water use and irrigation coverage; rainfall adequacy against requirement.

- Fertiliser consumption per hectare (N, P, K) and fertiliser-to-output efficiency.

- Land-use efficiency and share of fallow or unused land.

- Input cost per hectare and profit margin per crop.

## 4.4 Supporting External Factors

- Weather: rainfall, temperature and extreme-event indicators.

- Macro and policy: fuel prices, exchange rates, inflation, subsidies and trade policy.

- Demand: population growth, consumption trends and export demand.

# 5. Step-by-Step Plan

## Phase 1: Data Collection

- Finalise the list of crops, regions and years to be covered.

- Register or access each selected portal and download data as CSV/Excel, or retrieve it through APIs.

- Record metadata for every dataset: source, URL, download date, units, frequency and licence.

- Store raw files unchanged in a dedicated 'raw data' folder to keep the process reproducible.

## Phase 2: Data Cleaning and Preparation

- Inspect each dataset: structure, data types, ranges, duplicates and missing values.

- Standardise names of crops, states and markets, and convert all units (for example quintal to tonne).

- Handle missing values using interpolation, forward-fill or regional averages, and document each choice.

- Detect outliers with box plots and z-scores; verify against sources before removing or correcting them.

- Merge datasets on common keys (crop, region, date) and create derived features such as lagged prices, moving averages and seasonal indicators.

- Save the cleaned dataset to a separate 'processed data' folder.

## Phase 3: Exploratory Analysis and Modelling

- Run descriptive statistics and visualisations: line charts, seasonal plots, heat maps and correlation matrices.

- Decompose time series into trend, seasonality and residual components.

- Build baseline forecasts (naive and moving average) for comparison.

- Train and tune forecasting models, using time-based train/test splits and cross-validation.

- Evaluate models using MAE, RMSE and MAPE, and select the best performing approach.

## Phase 4: Interpretation and Reporting

- Interpret findings in business terms: which crops, regions and seasons show opportunity or risk.

- Check results against domain knowledge and known events such as droughts or policy changes.

- Present results through a dashboard and a final report with clear recommendations and stated limitations.

# 6. Proposed Analysis Methods

| Method | Purpose | Suitable For |
| --- | --- | --- |
| Descriptive statistics and visualisation | Understand distributions, trends and relationships | All metrics |
| Correlation and regression analysis | Quantify how weather, inputs and costs affect yield and price | Yield and price drivers |
| Time-series decomposition | Separate trend, seasonality and noise | Monthly and daily prices |
| ARIMA / SARIMA | Statistical forecasting of seasonal series | Short-term price forecasts |
| Prophet / Exponential smoothing | Robust forecasting with holidays and seasonality | Price and arrival forecasts |
| Random Forest / Gradient Boosting | Capture non-linear effects of many features | Yield prediction |
| LSTM (optional) | Deep-learning approach for long sequences | Extended forecasting experiments |
| Clustering (K-Means) | Group regions or crops with similar behaviour | Regional segmentation |

## 6.1 Tools and Technology

- Programming: Python (pandas, NumPy, scikit-learn, statsmodels, Prophet).

- Visualisation: Matplotlib, Seaborn, Plotly; Power BI or Tableau for dashboards.

- Environment and storage: Jupyter Notebook, Excel/CSV files, and GitHub for version control.

# 7. Timeline and Milestones

The work is planned over six weeks, with a clear milestone at the end of each stage.

| Week | Activities | Milestone | Output |
| --- | --- | --- | --- |
| Week 1 | Problem definition, scope, research of public sources, and preparation of this plan | Plan approved | Planning document |
| Week 2 | Download and organise datasets; record metadata; set up project folders | Raw data collected | Data inventory |
| Week 3 | Clean, standardise and merge data; handle missing values and outliers | Clean dataset ready | Processed dataset |
| Week 4 | Exploratory analysis, visualisations and trend and seasonality study | Insights identified | EDA notebook and charts |
| Week 5 | Build, tune and evaluate forecasting models | Best model selected | Forecast results |
| Week 6 | Interpret results, build dashboard, write report and recommendations | Final submission | Report and dashboard |

# 8. Risks and Mitigation

| Risk | Mitigation |
| --- | --- |
| Missing or inconsistent data | Cross-check multiple sources; use documented imputation; flag low-quality periods |
| Different units, formats and definitions | Create a unit-conversion table and a data dictionary |
| Data not updated on time | Use the latest available year and clearly state the data cut-off date |
| Weather shocks and policy changes causing sudden breaks | Include weather and policy variables; test models on volatile periods |
| Model overfitting | Use time-based validation, baseline comparison and simple models first |
| Schedule delays | Build buffer time into each phase and prioritise core crops first |

# 9. Expected Outcomes

- A clean, documented and reproducible dataset on crop yields, prices and resource use.

- A clear understanding of long-term trends, seasonality and key drivers in agriculture.

- Validated forecasting models for prices and yields with measured accuracy.

- Actionable insights for farmers, traders, agribusiness firms and policymakers.

- A final report and interactive dashboard that can be reused and updated.

# 10. Conclusion

This plan sets out a practical and organised approach to agribusiness data analysis. It identifies dependable public data sources, defines the metrics that matter (crop yields, pricing dynamics and resource utilization), describes a clear process for collection, cleaning and interpretation, and provides a realistic six-week timeline with milestones. Following this plan will allow the project to move from raw public data to forecasts and insights that support better decisions in the agricultural market.

Prepared by: Palarapu Harshavardhan Reddy

Intern